## ACR-01-MSDAT (hidden)
WBS | Task Name | Time | StartDate | EndDate | Predecessors | Successors
1 | ACCREDO ASIA PLANT EXPANSION PROJECT | 220 days | 2021-05-10 | 2021-12-15
1.1 | Key Milestones | 219 days | 2021-05-10 | 2021-12-15
1.1.1 | LOA is signed | 0 days | 2021-05-10 | 2021-05-10 |  | 21SS,6,4SS,15SS+6 days
1.1.2 | Take Over Site Date | 0 days | 2021-05-11 | 2021-05-11 | 3SS | 5
1.1.3 | CLIENT PROVIDE ENOUGH DOCUMENT FOR GET TEMPORARY PERMIT | 0 days | 2021-05-11 | 2021-05-11 | 4 | 6SS,22SS
1.1.4 | TEMPORARY CONSTRUCTION PREMIT | 10 days | 2021-05-11 | 2021-05-20 | 5SS,3 | 24FS+3 days,29,23,8,26,7
1.1.5 | CLIENT PROVIDE APPROVED CONSTRUCTION DRAWING FOR TEST PILE | 0 days | 2021-05-20 | 2021-05-20 | 6 | 8,26
1.1.6 | Commencement Date EARLY WORKS | 0 days | 2021-05-20 | 2021-05-20 | 6,7
1.1.7 | CLIENT PROVIDE APPROVED CONSTRUCTION DRAWING | 0 days | 2021-07-11 | 2021-07-11 |  | 46SS
1.1.8 | CLIENT GET 1/500 APPROVAL | 0 days | 2021-06-12 | 2021-06-12
1.1.9 | CLIENT PROVIDE CONSTRUCTION PERMIT | 0 days | 2021-07-11 | 2021-07-11 |  | 46SS
1.1.10 | Completion Date and Handover | 0 days | 2021-12-15 | 2021-12-15 | 44
1.2 | MEP Long Lead Items: Submit & Approve | 154 days | 2021-05-16 | 2021-10-17
1.2.1 | Preparation Works | 154 days | 2021-05-16 | 2021-10-17
1.2.1.1 | Submit Equipment Doccument | 10 days | 2021-05-16 | 2021-05-25 | 3SS+6 days | 16SS+7 days
1.2.1.2 | Consultant/Client review and approval (propose 7days after submission) | 10 days | 2021-05-23 | 2021-06-01 | 15SS+7 days | 17SS+7 days
1.2.1.3 | Submit copy doccument of "Place order" | 10 days | 2021-05-30 | 2021-06-08 | 16SS+7 days | 18FS+100 days
1.2.1.4 | Delivery to site | 30 days | 2021-09-18 | 2021-10-17 | 17FS+100 days
1.3 | EARLY WORK | 39 days | 2021-05-10 | 2021-06-17
1.3.1 | Preparation Works | 21 days | 2021-05-10 | 2021-05-30
1.3.1.1 | Set up Construction Management Team | 10 days | 2021-05-10 | 2021-05-19 | 3SS
1.3.1.2 | Method statement drawing submission for approval | 10 days | 2021-05-11 | 2021-05-20 | 5SS
1.3.1.3 | Temporary facilities/Install power and water sources | 10 days | 2021-05-21 | 2021-05-30 | 6
1.3.1.4 | Equipment Mobilization Works for test piles | 7 days | 2021-05-24 | 2021-05-30 | 6FS+3 days | 29
1.3.2 | Test piles | 28 days | 2021-05-21 | 2021-06-17
1.3.2.1 | Shopdrawing, Material sample submission and approval | 1 day | 2021-05-21 | 2021-05-21 | 6,7 | 27
1.3.2.2 | Testing piles manufacture | 1 day | 2021-05-22 | 2021-05-22 | 26 | 28
1.3.2.3 | Curing Test Piles | 7 days | 2021-05-23 | 2021-05-29 | 27 | 29
1.3.2.4 | Test pile delivery to site | 1 day | 2021-05-31 | 2021-05-31 | 28,6,24 | 30SS,32
1.3.2.5 | Press test pile D500 | 2 days | 2021-05-31 | 2021-06-01 | 29SS | 31
1.3.2.6 | Approval mass piles D500 by Client and Consultant | 1 day | 2021-06-02 | 2021-06-02 | 30 | 36
1.3.2.7 | Press test pile D350 | 1 day | 2021-06-01 | 2021-06-01 | 29 | 33FS+7 days
1.3.2.8 | Static load tests D350 (2 nos) | 6 days | 2021-06-09 | 2021-06-14 | 32FS+7 days | 34
1.3.2.9 | Test report D350 | 3 days | 2021-06-15 | 2021-06-17 | 33
1.4 | Pile manufacture | 30 days | 2021-06-03 | 2021-07-02
1.4.1 | Mass pile manufacture | 20 days | 2021-06-03 | 2021-06-22 | 31 | 37SS+10 days
1.4.2 | Mass pile delivery | 20 days | 2021-06-13 | 2021-07-02 | 36SS+10 days | 46SS
1.5 | Steel structure fabrication and deliver to site/ Chế tạo kết cấu thép và vận chuyển đến công trường | 93 days | 2021-07-05 | 2021-10-06
1.5.1 | Make steel structure shop drawing | 21 days | 2021-07-05 | 2021-07-25 | 59FS-100 days | 40SS
1.5.2 | Sample submission for steel structures | 14 days | 2021-07-05 | 2021-07-18 | 39SS | 41
1.5.3 | Client approve Shop dwgs | 14 days | 2021-07-19 | 2021-08-01 | 40 | 42
1.5.4 | Steel structure fabrication | 50 days | 2021-08-02 | 2021-09-21 | 41 | 43FS-15 days
1.5.5 | Steel structure delivery | 30 days | 2021-09-07 | 2021-10-06 | 42FS-15 days
1.6 | CONSTRUCTION MAIN WORK | 158 days | 2021-07-11 | 2021-12-15 |  | 12
1.6.1 | MASS PILE WORKS | 26 days | 2021-07-11 | 2021-08-05
1.6.1.1 | Pressing mass piles of Production | 16 days | 2021-07-11 | 2021-07-26 | 37SS,11SS,9SS | 50SS+10 days,47
1.6.1.2 | Pressing mass piles of Utilities | 10 days | 2021-07-27 | 2021-08-05 | 46 | 78
1.6.2 | PRODUCTION BUILDING | 148 days | 2021-07-21 | 2021-12-15
1.6.2.1 | R.C STRUCTURE | 70 days | 2021-07-21 | 2021-09-29
1.6.2.1.1 | Excavation, Pile headtreament | 20 days | 2021-07-21 | 2021-08-09 | 46SS+10 days | 51SS+6 days
1.6.2.1.2 | Lean concrete, rebar work, formwork and cast concrete for Foundation and Stump | 20 days | 2021-07-27 | 2021-08-15 | 50SS+6 days | 52FF+9 days,99SS,53SS+7 days
1.6.2.1.3 | Backfill | 25 days | 2021-07-31 | 2021-08-24 | 51FF+9 days | 54SS+5 days
1.6.2.1.4 | Excavation, Compaction Rock 5-40 type 2, type 1 | 25 days | 2021-08-03 | 2021-08-27 | 51SS+7 days
1.6.2.1.5 | Excavation top soil to bottom of rock layer | 25 days | 2021-08-05 | 2021-08-29 | 52SS+5 days | 55FF+8 days
1.6.2.1.6 | Formwork, Rebar, Cast concrete for column +0.000 to +7.500 | 25 days | 2021-08-13 | 2021-09-07 | 54FF+8 days | 56FF+12 days
1.6.2.1.7 | Formwork, Rebar, Cast concrete for level 2 slab +7.500 | 30 days | 2021-08-20 | 2021-09-19 | 55FF+12 days | 57FF+10 days,76SS,62SS+17 days
1.6.2.1.8 | Formwork, Rebar, Cast concrete for column +7.500 to +13.600 | 25 days | 2021-09-05 | 2021-09-29 | 56FF+10 days | 59FF+14 days
1.6.2.2 | Install steel structure | 39 days | 2021-09-29 | 2021-11-06
1.6.2.2.1 | Rafter; Purlins; Bracing installation axis 1-17/A-G | 15 days | 2021-09-29 | 2021-10-13 | 57FF+14 days | 60FS-3 days,62SS+3 days,39FS-100 days
1.6.2.2.2 | Roof sheet installation | 12 days | 2021-10-11 | 2021-10-22 | 59FS-3 days | 71SS+10 days,61
1.6.2.2.3 | Flashing, trimming, gutter, downspout installation | 15 days | 2021-10-23 | 2021-11-06 | 60
1.6.2.3 | Lean concrete, rebar work, formwork and cast concrete for ground floor +0.000 | 30 days | 2021-10-02 | 2021-10-31 | 56SS+17 days,59SS+3 days | 65SS+14 days
1.6.2.4 | Finishing works | 61 days | 2021-10-16 | 2021-12-15
1.6.2.4.1 | Level 1 | 57 days | 2021-10-16 | 2021-12-11
1.6.2.4.1.1 | Brick wall | 40 days | 2021-10-16 | 2021-11-24 | 62SS+14 days | 66SS+10 days
1.6.2.4.1.2 | Painting and tiling wall/ finishing wall | 40 days | 2021-10-26 | 2021-12-04 | 65SS+10 days | 68SS+10 days
1.6.2.4.1.3 | Floor finishing work | 25 days | 2021-11-12 | 2021-12-06 | 68SS+7 days | 69
1.6.2.4.1.4 | Door and windown | 22 days | 2021-11-05 | 2021-11-26 | 66SS+10 days | 67SS+7 days,90
1.6.2.4.1.5 | Other works | 5 days | 2021-12-07 | 2021-12-11 | 67
1.6.2.4.2 | Level 2 | 56 days | 2021-10-21 | 2021-12-15
1.6.2.4.2.1 | Brick wall | 40 days | 2021-10-21 | 2021-11-29 | 60SS+10 days | 72SS+10 days
1.6.2.4.2.2 | Painting and tiling wall/ finishing wall | 40 days | 2021-10-31 | 2021-12-09 | 71SS+10 days | 74SS+10 days
1.6.2.4.2.3 | Floor finishing work | 24 days | 2021-11-17 | 2021-12-10 | 74SS+7 days | 75
1.6.2.4.2.4 | Door and windown | 21 days | 2021-11-10 | 2021-11-30 | 72SS+10 days | 73SS+7 days
1.6.2.4.2.5 | Other works | 5 days | 2021-12-11 | 2021-12-15 | 73
1.6.2.5 | Mep installation works | 115 days | 2021-08-20 | 2021-12-13 | 56SS
1.6.3 | UTILITIES BUILDING | 122 days | 2021-08-06 | 2021-12-06
1.6.3.1 | Excavation, Lean Concrete, Rebar, Cast Concrete of Foundation | 20 days | 2021-08-06 | 2021-08-25 | 47 | 79,85
1.6.3.2 | Rebar, Formwork, Cast Concrete of Column GF to level 2 | 7 days | 2021-08-26 | 2021-09-01 | 78 | 80
1.6.3.3 | Formwork, Rebar, Cast Concrete of Level 2 slab at +7.500 | 10 days | 2021-09-03 | 2021-09-12 | 79 | 81
1.6.3.4 | Rebar, Formwork, Cast Concrete of Column level 2 to roof | 5 days | 2021-09-13 | 2021-09-17 | 80 | 82
1.6.3.5 | Formwork, Rebar, Cast Concrete of Roof at level +11.500 | 10 days | 2021-09-18 | 2021-09-27 | 81 | 83
1.6.3.6 | Finishing work | 70 days | 2021-09-28 | 2021-12-06 | 82
1.6.4 | WASTE STORAGE | 64 days | 2021-08-26 | 2021-10-29
1.6.4.1 | Excavation, Lean Concrete, Rebar, Cast Concrete of Foundation | 20 days | 2021-08-26 | 2021-09-15 | 78 | 86
1.6.4.2 | Rebar, Formwork, Cast Concrete of Column GF to level 2 | 6 days | 2021-09-16 | 2021-09-21 | 85 | 87
1.6.4.3 | Installtion steel purlin and metal roof | 8 days | 2021-09-22 | 2021-09-29 | 86 | 88
1.6.4.4 | Finishing work | 30 days | 2021-09-30 | 2021-10-29 | 87
1.6.5 | DEFECT AND HANDOVER PROJECT | 30 days | 2021-11-16 | 2021-12-15
1.6.5.1 | Testing and Commissioning | 19 days | 2021-11-27 | 2021-12-15 | 68 | 91FF
1.6.5.2 | Defect and Handover | 30 days | 2021-11-16 | 2021-12-15 | 90FF | 100FF-25 days
2 | 1 | 191 days | 2021-05-13 | 2021-11-21
2.1 | Cau di dong 1 | 0 days | 2021-05-13 | 2021-05-13
2.1.1 | 1 | 0 days | 2021-05-13 | 2021-05-13
2.1.2 | 2 | 0 days | 2021-05-13 | 2021-05-13
2.2 | Cau di dong 2 | 191 days | 2021-05-13 | 2021-11-21
2.2.1 | 1 | 0 days | 2021-07-27 | 2021-07-27 | 51SS
2.2.2 | 2 | 0 days | 2021-11-21 | 2021-11-21 | 91FF-25 days
2.2.3 |  | 0 days | 2021-05-13 | 2021-05-13

## 02-CODE
MÃ DỰ ÁN | MÃ BỘ MÔN | MÃ ZONE | MÃ TẦNG | MÃ LOẠI | MÃ THI CÔNG | MÔ TẢ NGẮN EN | MÔ TẢ NGẮN VI | WORK ITEM NUMBER | WBS | Task Name | Time | Start | Finish | Predecessors | Successors | Text1 | Text2
[8 empty] | ----- | 1 | ACCREDO ASIA PLANT EXPANSION PROJECT | 220 days | 2021-05-10 | 2021-12-15
[8 empty] | ----- | 1.1 | Key Milestones | 219 days | 2021-05-10 | 2021-12-15
[8 empty] | ----- | 1.1.1 | LOA is signed | 0 days | 2021-05-10 | 2021-05-10
[8 empty] | ----- | 1.1.2 | Take Over Site Date | 0 days | 2021-05-11 | 2021-05-11
[8 empty] | ----- | 1.1.3 | CLIENT PROVIDE ENOUGH DOCUMENT FOR GET TEMPORARY PERMIT | 0 days | 2021-05-11 | 2021-05-11
[8 empty] | ----- | 1.1.4 | TEMPORARY CONSTRUCTION PREMIT | 10 days | 2021-05-11 | 2021-05-20
[8 empty] | ----- | 1.1.5 | CLIENT PROVIDE APPROVED CONSTRUCTION DRAWING FOR TEST PILE | 0 days | 2021-05-20 | 2021-05-20
[8 empty] | ----- | 1.1.6 | Commencement Date EARLY WORKS | 0 days | 2021-05-20 | 2021-05-20
[8 empty] | ----- | 1.1.7 | CLIENT PROVIDE APPROVED CONSTRUCTION DRAWING | 0 days | 2021-07-11 | 2021-07-11
[8 empty] | ----- | 1.1.8 | CLIENT GET 1/500 APPROVAL | 0 days | 2021-06-12 | 2021-06-12
[8 empty] | ----- | 1.1.9 | CLIENT PROVIDE CONSTRUCTION PERMIT | 0 days | 2021-07-11 | 2021-07-11
[8 empty] | ----- | 1.1.10 | Completion Date and Handover | 0 days | 2021-12-15 | 2021-12-15
[8 empty] | ----- | 1.2 | MEP Long Lead Items: Submit & Approve | 154 days | 2021-05-16 | 2021-10-17
[8 empty] | ----- | 1.2.1 | Preparation Works | 154 days | 2021-05-16 | 2021-10-17
[8 empty] | ----- | 1.2.1.1 | Submit Equipment Doccument | 10 days | 2021-05-16 | 2021-05-25
[8 empty] | ----- | 1.2.1.2 | Consultant/Client review and approval (propose 7days after submission) | 10 days | 2021-05-23 | 2021-06-01
[8 empty] | ----- | 1.2.1.3 | Submit copy doccument of "Place order" | 10 days | 2021-05-30 | 2021-06-08
[8 empty] | ----- | 1.2.1.4 | Delivery to site | 30 days | 2021-09-18 | 2021-10-17
[8 empty] | ----- | 1.3 | EARLY WORK | 39 days | 2021-05-10 | 2021-06-17
[8 empty] | ----- | 1.3.1 | Preparation Works | 21 days | 2021-05-10 | 2021-05-30
[8 empty] | ----- | 1.3.1.1 | Set up Construction Management Team | 10 days | 2021-05-10 | 2021-05-19
[8 empty] | ----- | 1.3.1.2 | Method statement drawing submission for approval | 10 days | 2021-05-11 | 2021-05-20
[8 empty] | ----- | 1.3.1.3 | Temporary facilities/Install power and water sources | 10 days | 2021-05-21 | 2021-05-30
[8 empty] | ----- | 1.3.1.4 | Equipment Mobilization Works for test piles | 7 days | 2021-05-24 | 2021-05-30
ACR | S | ZZ | GF | PL | PW TP | TEST PILE |  | ACR-S-ZZ-GF-PL-PW TP | 1.3.2 | Test piles | 28 days | 2021-05-21 | 2021-06-17
[8 empty] | ----- | 1.3.2.1 | Shopdrawing, Material sample submission and approval | 1 day | 2021-05-21 | 2021-05-21
[8 empty] | ----- | 1.3.2.2 | Testing piles manufacture | 1 day | 2021-05-22 | 2021-05-22
[8 empty] | ----- | 1.3.2.3 | Curing Test Piles | 7 days | 2021-05-23 | 2021-05-29
[8 empty] | ----- | 1.3.2.4 | Test pile delivery to site | 1 day | 2021-05-31 | 2021-05-31
ACR | S | ZZ | GF | PL | PW TP D500 | TEST PILE D500 |  | ACR-S-ZZ-GF-PL-PW TP D500 | 1.3.2.5 | Press test pile D500 | 2 days | 2021-05-31 | 2021-06-01
[8 empty] | ----- | 1.3.2.6 | Approval mass piles D500 by Client and Consultant | 1 day | 2021-06-02 | 2021-06-02
[8 empty] | ----- | 1.3.2.7 | Press test pile D350 | 1 day | 2021-06-01 | 2021-06-01
ACR | S | ZZ | GF | PL | PW TP D350 | TEST PILE D350 |  | ACR-S-ZZ-GF-PL-PW TP D350 | 1.3.2.8 | Static load tests D350 (2 nos) | 6 days | 2021-06-09 | 2021-06-14
[8 empty] | ----- | 1.3.2.9 | Test report D350 | 3 days | 2021-06-15 | 2021-06-17
[8 empty] | ----- | 1.4 | Pile manufacture | 30 days | 2021-06-03 | 2021-07-02
[8 empty] | ----- | 1.4.1 | Mass pile manufacture | 20 days | 2021-06-03 | 2021-06-22
[8 empty] | ----- | 1.4.2 | Mass pile delivery | 20 days | 2021-06-13 | 2021-07-02
[8 empty] | ----- | 1.5 | Steel structure fabrication and deliver to site/ Chế tạo kết cấu thép và vận chuyển đến công trường | 93 days | 2021-07-05 | 2021-10-06
[8 empty] | ----- | 1.5.1 | Make steel structure shop drawing | 21 days | 2021-07-05 | 2021-07-25
[8 empty] | ----- | 1.5.2 | Sample submission for steel structures | 14 days | 2021-07-05 | 2021-07-18
[8 empty] | ----- | 1.5.3 | Client approve Shop dwgs | 14 days | 2021-07-19 | 2021-08-01
[8 empty] | ----- | 1.5.4 | Steel structure fabrication | 50 days | 2021-08-02 | 2021-09-21
[8 empty] | ----- | 1.5.5 | Steel structure delivery | 30 days | 2021-09-07 | 2021-10-06
[8 empty] | ----- | 1.6 | CONSTRUCTION MAIN WORK | 158 days | 2021-07-11 | 2021-12-15
[8 empty] | ----- | 1.6.1 | MASS PILE WORKS | 26 days | 2021-07-11 | 2021-08-05
ACR | S | FA | GF | PL | PW MP |  |  | ACR-S-FA-GF-PL-PW MP | 1.6.1.1 | Pressing mass piles of Production | 16 days | 2021-07-11 | 2021-07-26
ACR | S | UT | GF | PL | PW MP |  |  | ACR-S-UT-GF-PL-PW MP | 1.6.1.2 | Pressing mass piles of Utilities | 10 days | 2021-07-27 | 2021-08-05
[8 empty] | ----- | 1.6.2 | PRODUCTION BUILDING | 148 days | 2021-07-21 | 2021-12-15
[8 empty] | ----- | 1.6.2.1 | R.C STRUCTURE | 70 days | 2021-07-21 | 2021-09-29
[8 empty] | ----- | 1.6.2.1.1 | Excavation, Pile headtreament | 20 days | 2021-07-21 | 2021-08-09
ACR | S | ZZ | GF | ZZ | CR | CONCRETE FOUNDATION & STUMP |  | ACR-S-ZZ-GF-ZZ-CR | 1.6.2.1.2 | Lean concrete, rebar work, formwork and cast concrete for Foundation and Stump | 20 days | 2021-07-27 | 2021-08-15
[8 empty] | ----- | 1.6.2.1.3 | Backfill | 25 days | 2021-07-31 | 2021-08-24
[8 empty] | ----- | 1.6.2.1.4 | Excavation, Compaction Rock 5-40 type 2, type 1 | 25 days | 2021-08-03 | 2021-08-27
[8 empty] | ----- | 1.6.2.1.5 | Excavation top soil to bottom of rock layer | 25 days | 2021-08-05 | 2021-08-29
ACR | S | FA | 1F | CL | CR | CONCRETE COLUMN 01F |  | ACR-S-FA-1F-CL-CR | 1.6.2.1.6 | Formwork, Rebar, Cast concrete for column +0.000 to +7.500 | 25 days | 2021-08-13 | 2021-09-07
ACR | S | FA | 2F | SL | CR | CONCRETE SLAB 02F |  | ACR-S-FA-2F-SL-CR | 1.6.2.1.7 | Formwork, Rebar, Cast concrete for level 2 slab +7.500 | 30 days | 2021-08-20 | 2021-09-19
ACR | S | FA | 2F | CL | CR |  |  | ACR-S-FA-2F-CL-CR | 1.6.2.1.8 | Formwork, Rebar, Cast concrete for column +7.500 to +13.600 | 25 days | 2021-09-05 | 2021-09-29
ACR | S | FA | 3F | CL | SE | STEEL |  | ACR-S-FA-3F-CL-SE | 1.6.2.2 | Install steel structure | 39 days | 2021-09-29 | 2021-11-06
ACR | S | FA | RF | RO | SE FR | STEEL FRAME |  | ACR-S-FA-RF-RO-SE FR | 1.6.2.2.1 | Rafter; Purlins; Bracing installation axis 1-17/A-G | 15 days | 2021-09-29 | 2021-10-13
ACR | S | FA | RF | RO | SE RS | ROOF METAL SHEET |  | ACR-S-FA-RF-RO-SE RS | 1.6.2.2.2 | Roof sheet installation | 12 days | 2021-10-11 | 2021-10-22
ARC | S | FA | RF | RO | SE ZZ | FLASHING, TRIMMING, GUTTER,DOUSPOUT |  | ARC-S-FA-RF-RO-SE ZZ | 1.6.2.2.3 | Flashing, trimming, gutter, downspout installation | 15 days | 2021-10-23 | 2021-11-06
ARC | S | FA | 1F | SL | CR | CONCRETE SLAB 01F |  | ARC-S-FA-1F-SL-CR | 1.6.2.3 | Lean concrete, rebar work, formwork and cast concrete for ground floor +0.000 | 30 days | 2021-10-02 | 2021-10-31
[8 empty] | ----- | 1.6.2.4 | Finishing works | 61 days | 2021-10-16 | 2021-12-15
[8 empty] | ----- | 1.6.2.4.1 | Level 1 | 57 days | 2021-10-16 | 2021-12-11
[8 empty] | ----- | 1.6.2.4.1.1 | Brick wall | 40 days | 2021-10-16 | 2021-11-24
[8 empty] | ----- | 1.6.2.4.1.2 | Painting and tiling wall/ finishing wall | 40 days | 2021-10-26 | 2021-12-04
[8 empty] | ----- | 1.6.2.4.1.3 | Floor finishing work | 25 days | 2021-11-12 | 2021-12-06
[8 empty] | ----- | 1.6.2.4.1.4 | Door and windown | 22 days | 2021-11-05 | 2021-11-26
[8 empty] | ----- | 1.6.2.4.1.5 | Other works | 5 days | 2021-12-07 | 2021-12-11
[8 empty] | ----- | 1.6.2.4.2 | Level 2 | 56 days | 2021-10-21 | 2021-12-15
[8 empty] | ----- | 1.6.2.4.2.1 | Brick wall | 40 days | 2021-10-21 | 2021-11-29
[8 empty] | ----- | 1.6.2.4.2.2 | Painting and tiling wall/ finishing wall | 40 days | 2021-10-31 | 2021-12-09
[8 empty] | ----- | 1.6.2.4.2.3 | Floor finishing work | 24 days | 2021-11-17 | 2021-12-10
[8 empty] | ----- | 1.6.2.4.2.4 | Door and windown | 21 days | 2021-11-10 | 2021-11-30
[8 empty] | ----- | 1.6.2.4.2.5 | Other works | 5 days | 2021-12-11 | 2021-12-15
[8 empty] | ----- | 1.6.2.5 | Mep installation works | 115 days | 2021-08-20 | 2021-12-13
[8 empty] | ----- | 1.6.3 | UTILITIES BUILDING | 122 days | 2021-08-06 | 2021-12-06
[8 empty] | ----- | 1.6.3.1 | Excavation, Lean Concrete, Rebar, Cast Concrete of Foundation | 20 days | 2021-08-06 | 2021-08-25
[8 empty] | ----- | 1.6.3.2 | Rebar, Formwork, Cast Concrete of Column GF to level 2 | 7 days | 2021-08-26 | 2021-09-01
[8 empty] | ----- | 1.6.3.3 | Formwork, Rebar, Cast Concrete of Level 2 slab at +7.500 | 10 days | 2021-09-03 | 2021-09-12
[8 empty] | ----- | 1.6.3.4 | Rebar, Formwork, Cast Concrete of Column level 2 to roof | 5 days | 2021-09-13 | 2021-09-17
[8 empty] | ----- | 1.6.3.5 | Formwork, Rebar, Cast Concrete of Roof at level +11.500 | 10 days | 2021-09-18 | 2021-09-27
[8 empty] | ----- | 1.6.3.6 | Finishing work | 70 days | 2021-09-28 | 2021-12-06
[8 empty] | ----- | 1.6.4 | WASTE STORAGE | 64 days | 2021-08-26 | 2021-10-29
[8 empty] | ----- | 1.6.4.1 | Excavation, Lean Concrete, Rebar, Cast Concrete of Foundation | 20 days | 2021-08-26 | 2021-09-15
[8 empty] | ----- | 1.6.4.2 | Rebar, Formwork, Cast Concrete of Column GF to level 2 | 6 days | 2021-09-16 | 2021-09-21
[8 empty] | ----- | 1.6.4.3 | Installtion steel purlin and metal roof | 8 days | 2021-09-22 | 2021-09-29
[8 empty] | ----- | 1.6.4.4 | Finishing work | 30 days | 2021-09-30 | 2021-10-29
[8 empty] | ----- | 1.6.5 | DEFECT AND HANDOVER PROJECT | 30 days | 2021-11-16 | 2021-12-15
[8 empty] | ----- | 1.6.5.1 | Testing and Commissioning | 19 days | 2021-11-27 | 2021-12-15
[8 empty] | ----- | 1.6.5.2 | Defect and Handover | 30 days | 2021-11-16 | 2021-12-15
[8 empty] | ----- | 2 | 1 | 191 days | 2021-05-13 | 2021-11-21
[8 empty] | ----- | 2.1 | Cau di dong 1 | 0 days | 2021-05-13 | 2021-05-13
[8 empty] | ----- | 2.1.1 | 1 | 0 days | 2021-05-13 | 2021-05-13
[8 empty] | ----- | 2.1.2 | 2 | 0 days | 2021-05-13 | 2021-05-13
[8 empty] | ----- | 2.2 | Cau di dong 2 | 191 days | 2021-05-13 | 2021-11-21
[8 empty] | ----- | 2.2.1 | 1 | 0 days | 2021-07-27 | 2021-07-27
[8 empty] | ----- | 2.2.2 | 2 | 0 days | 2021-11-21 | 2021-11-21
[8 empty] | ----- | 2.2.3 | 0 | 0 days | 2021-05-13 | 2021-05-13
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | ----- | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Formulas:
Start = ACR_01_MSDAT__2[[#This Row],[StartDate]]
Finish = ACR_01_MSDAT__2[[#This Row],[EndDate]]
1
2
3
4
5
6
7
8

## BAK (hidden)
SS | S
SS | S | PD
SS | S | PD | 02F
SS | S | PD | 02F | ZZ | SC
SS | S | PD | 02F | CL | SC ZA
SS | S | PD | 02F | CL | SC ZB
SS | S | PD | 02F | CL | SC ZC
SS | S | PD | 02F | CL | SC ZD
SS | S | PD | 02F | SW | SC
SS | S | PD | 02F | ZZ | RB
SS | S | PD | 02F | CL | RB ZA
SS | S | PD | 02F | CL | RB ZB
SS | S | PD | 02F | CL | RB ZC
SS | S | PD | 02F | CL | RB ZD
SS | S | PD | 02F | SW | RB
SS | S | PD | 02F | ZZ | FW
SS | S | PD | 02F | CL | FW ZA
SS | S | PD | 02F | CL | FW ZB
SS | S | PD | 02F | CL | FW ZC
SS | S | PD | 02F | CL | FW ZD
SS | S | PD | 02F | SW | FW
SS | S | PD | 02F | ZZ | SP
SS | S | PD | 02F | SL | SP ZA
SS | S | PD | 02F | SL | SP ZB
SS | S | PD | 02F | SL | SP ZC
SS | S | PD | 02F | SL | SP ZD
SS | S | PD | 02F | SL | FW
SS | S | PD | 02F | SL | FW ZA
SS | S | PD | 02F | SL | FW ZB
SS | S | PD | 02F | SL | FW ZC
SS | S | PD | 02F | SL | FW ZD
SS | S | PD | 02F | SL | RB
SS | S | PD | 02F | SL | RB ZA
SS | S | PD | 02F | SL | RB ZB
SS | S | PD | 02F | SL | RB ZC
SS | S | PD | 02F | SL | RB ZD