## WorkItemData
WI Number | Task Name | Start | Finish
- | ACCREDO ASIA PLANT EXPANSION PROJECT | 5/10/2021 | 12/15/2021
ACR-S-ZZ-GF-PL-PW TP | Test piles | 5/21/2021 | 6/17/2021
ACR-S-ZZ-GF-PL-PW TP D500 | Press test pile D500 | 5/31/2021 | 6/1/2021
ACR-S-ZZ-GF-PL-PW TP D350 | Static load tests D350 (2 nos) | 6/9/2021 | 6/14/2021
ACR-S-FA-GF-PL-PW MP | Pressing mass piles of Production | 7/11/2021 | 7/26/2021
ACR-S-UT-GF-PL-PW MP | Pressing mass piles of Utilities | 7/27/2021 | 8/5/2021
ACR-S-ZZ-GF-ZZ-CR | Lean concrete, rebar work, formwork and cast concrete for Foundation and Stump | 7/27/2021 | 8/15/2021
ACR-S-FA-1F-CL-CR | Formwork, Rebar, Cast concrete for column +0.000 to +7.500 | 8/13/2021 | 9/7/2021
ACR-S-FA-2F-SL-CR | Formwork, Rebar, Cast concrete for level 2 slab +7.500 | 8/20/2021 | 9/19/2021
ACR-S-FA-2F-CL-CR | Formwork, Rebar, Cast concrete for column +7.500 to +13.600 | 9/5/2021 | 9/29/2021
ACR-S-FA-3F-CL-SE | Install steel structure | 9/29/2021 | 11/6/2021
ACR-S-FA-RF-RO-SE FR | Rafter; Purlins; Bracing installation axis 1-17/A-G | 9/29/2021 | 10/13/2021
ACR-S-FA-RF-RO-SE RS | Roof sheet installation | 10/11/2021 | 10/22/2021
ARC-S-FA-RF-RO-SE ZZ | Flashing, trimming, gutter, downspout installation | 10/23/2021 | 11/6/2021
ARC-S-FA-1F-SL-CR | Lean concrete, rebar work, formwork and cast concrete for ground floor +0.000 | 10/2/2021 | 10/31/2021

## BACKUP (hidden)
WORK ITEM NUMBER | DESCRIPTION | Start | Finish | Actual Start Date | Acutal End Date / Actual Tracking date | PIC | #NCR | % Complete | Report Date | Quantity Unit | BIM Quantity | QS Quantity | Cost
| CONSTRUCTION WORKS | 26/04/21 | 31/07/22
S---- | Structure works | 02/05/21 | 28/04/22
S-PD--- | Podium | 02/05/21 | 20/08/21
S-PD-02F-- | Level 2 | 02/05/21 | 10/06/21
S-PD-02F-ZZ-CR | Concreting | 10/05/21 | 10/06/21
S-PD-02F-CL-CR ZA | Zone A - Column | 10/05/21 | 15/05/21
S-PD-02F-CL-CR ZA B1 | 1st batch | 10/05/21 | 10/05/21
S-PD-02F-CL-CR ZA B2 | 2nd batch | 12/05/21 | 12/05/21
S-PD-02F-CL-CR ZA B3 | 3rd batch | 15/05/21 | 15/05/21
S-PD-02F-CL-CR ZB | Zone B - Column | 13/05/21 | 17/05/21
S-PD-02F-CL-CR ZB B1 | 1st batch | 13/05/21 | 13/05/21
S-PD-02F-CL-CR ZB B2 | 2nd batch | 15/05/21 | 15/05/21
S-PD-02F-CL-CR ZB B3 | 3rd batch | 17/05/21 | 17/05/21
S-PD-02F-CL-CR ZC | Zone C - Column | 15/05/21 | 19/05/21
S-PD-02F-CL-CR ZC B1 | 1st batch | 15/05/21 | 15/05/21
S-PD-02F-CL-CR ZC B2 | 2nd batch | 17/05/21 | 17/05/21
S-PD-02F-CL-CR ZC B3 | 3rd batch | 19/05/21 | 19/05/21
S-PD-02F-CL-CR ZD | Zone D - Column | 17/05/21 | 21/05/21
S-PD-02F-CL-CR ZD B1 | 1st batch | 17/05/21 | 17/05/21
S-PD-02F-CL-CR ZD B2 | 2nd batch | 19/05/21 | 19/05/21
S-PD-02F-CL-CR ZD B3 | 3rd batch | 21/05/21 | 21/05/21
S-PD-02F-SW-CR | Core wall | 18/05/21 | 23/05/21
S-PD-02F-SW-CR zz B1 | 1st batch | 18/05/21 | 18/05/21
S-PD-02F-SW-CR zz B2 | 2nd batch | 23/05/21 | 23/05/21
S-PD-02F-SL-CR ZA | Zone A - Slab / beam | 01/06/21 | 01/06/21
S-PD-02F-SL-CR ZB | Zone B - Slab / beam | 03/06/21 | 03/06/21
S-PD-02F-SL-CR ZC | Zone C - Slab / beam | 07/06/21 | 07/06/21
S-PD-02F-SL-CR ZD | Zone D - Slab / beam | 10/06/21 | 10/06/21
S-PD-03F-- | Level 3 | 11/06/21 | 16/07/21
S-PD-03F-ZZ-CR | Concreting | 19/06/21 | 16/07/21
S-PD-03F-CL-CR ZA | Zone A - Column | 19/06/21 | 25/06/21
S-PD-03F-CL-CR ZA B1 | 1st batch | 19/06/21 | 19/06/21
S-PD-03F-CL-CR ZA B2 | 2nd batch | 21/06/21 | 21/06/21
S-PD-03F-CL-CR ZA B3 | 3rd batch | 25/06/21 | 25/06/21
S-PD-03F-CL-CR ZB | Zone B - Column | 22/06/21 | 27/06/21
S-PD-03F-CL-CR ZB B1 | 1st batch | 22/06/21 | 22/06/21
S-PD-03F-CL-CR ZB B2 | 2nd batch | 24/06/21 | 24/06/21
S-PD-03F-CL-CR ZB B3 | 3rd batch | 27/06/21 | 27/06/21
S-PD-03F-CL-CR ZC | Zone C - Column | 23/06/21 | 28/06/21
S-PD-03F-CL-CR ZC B1 | 1st batch | 23/06/21 | 23/06/21
S-PD-03F-CL-CR ZC B2 | 2nd batch | 25/06/21 | 25/06/21
S-PD-03F-CL-CR ZC B3 | 3rd batch | 28/06/21 | 28/06/21
S-PD-03F-CL-CR ZD | Zone D - Column | 25/06/21 | 29/06/21
S-PD-03F-CL-CR ZD B1 | 1st batch | 25/06/21 | 25/06/21
S-PD-03F-CL-CR ZD B2 | 2nd batch | 27/06/21 | 27/06/21
S-PD-03F-CL-CR ZD B3 | 3rd batch | 29/06/21 | 29/06/21
S-PD-03F-SW-CR | Core wall | 27/06/21 | 02/07/21
S-PD-03F-SW-CR zz B1 | 1st batch | 27/06/21 | 27/06/21
S-PD-03F-SW-CR zz B2 | 2nd batch | 02/07/21 | 02/07/21
S-PD-03F-SL-CR ZA | Zone A - Slab / beam | 10/07/21 | 10/07/21
S-PD-03F-SL-CR ZB | Zone B - Slab / beam | 12/07/21 | 12/07/21
S-PD-03F-SL-CR ZC | Zone C - Slab / beam | 16/07/21 | 16/07/21
S-PD-03F-SL-CR ZD | Zone D - Slab / beam | 15/07/21 | 15/07/21
S-PD-04F-- | Level 4 | 20/07/21 | 20/08/21
S-PD-04F-ZZ-CR | Concreting | 26/07/21 | 20/08/21
S-PD-04F-CL-CR ZA | Zone A - Column | 28/07/21 | 02/08/21
S-PD-04F-CL-CR ZA B1 | 1st batch | 28/07/21 | 28/07/21
S-PD-04F-CL-CR ZA B2 | 2nd batch | 30/07/21 | 30/07/21
S-PD-04F-CL-CR ZA B3 | 3rd batch | 02/08/21 | 02/08/21
S-PD-04F-CL-CR ZB | Zone B - Column | 26/07/21 | 30/07/21
S-PD-04F-CL-CR ZB B1 | 1st batch | 26/07/21 | 26/07/21
S-PD-04F-CL-CR ZB B2 | 2nd batch | 28/07/21 | 28/07/21
S-PD-04F-CL-CR ZB B3 | 3rd batch | 30/07/21 | 30/07/21
S-PD-04F-CL-CR ZC | Zone C - Column | 28/07/21 | 01/08/21
S-PD-04F-CL-CR ZC B1 | 1st batch | 28/07/21 | 28/07/21
S-PD-04F-CL-CR ZC B2 | 2nd batch | 30/07/21 | 30/07/21
S-PD-04F-CL-CR ZC B3 | 3rd batch | 01/08/21 | 01/08/21
S-PD-04F-CL-CR ZD | Zone D - Column | 29/07/21 | 02/08/21
S-PD-04F-CL-CR ZD B1 | 1st batch | 29/07/21 | 29/07/21
S-PD-04F-CL-CR ZD B2 | 2nd batch | 31/07/21 | 31/07/21
S-PD-04F-CL-CR ZD B3 | 3rd batch | 02/08/21 | 02/08/21
S-PD-04F-SW-CR | Core wall | 05/08/21 | 10/08/21
S-PD-04F-SW-CR zz B1 | 1st batch | 05/08/21 | 05/08/21
S-PD-04F-SW-CR zz B2 | 2nd batch | 10/08/21 | 10/08/21
S-PD-04F-SL-CR ZA | Zone A - Slab / beam | 19/08/21 | 19/08/21
S-PD-04F-SL-CR ZB | Zone B - Slab / beam | 16/08/21 | 16/08/21
S-PD-04F-SL-CR ZC | Zone C - Slab / beam | 20/08/21 | 20/08/21
S-PD-04F-SL-CR ZD | Zone D - Slab / beam | 20/08/21 | 20/08/21
S-TW--- | Tower | 21/08/21 | 28/04/22
S-TW-05F-- | Level 5 | 21/08/21 | 22/09/21
S-TW-05F-ZZ-CR | Concreting | 31/08/21 | 22/09/21
S-TW-05F-CL-CR ZA | Zone A - Column | 31/08/21 | 05/09/21
S-TW-05F-CL-CR ZA B1 | 1st batch | 31/08/21 | 31/08/21
S-TW-05F-CL-CR ZA B2 | 2nd batch | 05/09/21 | 05/09/21
S-TW-05F-CL-CR ZB | Zone B - Column | 03/09/21 | 07/09/21
S-TW-05F-CL-CR ZB B1 | 1st batch | 03/09/21 | 03/09/21
S-TW-05F-CL-CR ZB B2 | 2nd batch | 07/09/21 | 07/09/21
S-TW-05F-SW-CR | Core wall | 08/09/21 | 11/09/21
S-TW-05F-SW-CR ZZ B1 | 1st batch | 08/09/21 | 08/09/21
S-TW-05F-SW-CR ZZ B2 | 2nd batch | 11/09/21 | 11/09/21
S-TW-05F-SL BM-CR ZA | Zone A - Slab / beam | 20/09/21 | 20/09/21
S-TW-05F-SL BM-CR ZB | Zone B - Slab / beam | 22/09/21 | 22/09/21
S-TW-06F-- | Level 6 | 23/09/21 | 17/10/21
S-TW-06F-ZZ-CR | Concreting | 16/10/21 | 17/10/21
S-TW-06F-SL BM-CR ZA | Zone A - Slab / beam | 16/10/21 | 16/10/21
S-TW-06F-SL BM-CR ZB | Zone B - Slab / beam | 17/10/21 | 17/10/21
S-TW-07F-- | Level 7 | 17/10/21 | 05/11/21
S-TW-07F-ZZ-CR | Concreting | 02/11/21 | 05/11/21
S-TW-07F-SL BM-CR ZA | Zone A - Slab / beam | 02/11/21 | 02/11/21
S-TW-07F-SL BM-CR ZB | Zone B - Slab / beam | 05/11/21 | 05/11/21
S-TW-08F-- | Level 8 | 03/11/21 | 20/11/21
S-TW-08F-ZZ-CR | Concreting | 17/11/21 | 20/11/21
S-TW-08F-SL BM-CR ZA | Zone A - Slab / beam | 17/11/21 | 17/11/21
S-TW-08F-SL BM-CR ZB | Zone B - Slab / beam | 20/11/21 | 20/11/21
S-TW-09F-- | Level 9 | 18/11/21 | 03/12/21
S-TW-09F-ZZ-CR | Concreting | 30/11/21 | 03/12/21
S-TW-09F-SL BM-CR ZA | Zone A - Slab / beam | 30/11/21 | 30/11/21
S-TW-09F-SL BM-CR ZB | Zone B - Slab / beam | 03/12/21 | 03/12/21
S-TW-10F-- | Level 10 | 01/12/21 | 16/12/21
S-TW-10F-ZZ-CR | Concreting | 13/12/21 | 16/12/21
S-TW-10F-SL BM-CR ZA | Zone A - Slab / beam | 13/12/21 | 13/12/21
S-TW-10F-SL BM-CR ZB | Zone B - Slab / beam | 16/12/21 | 16/12/21
S-TW-11F-- | Level 11 | 14/12/21 | 29/12/21
S-TW-11F-ZZ-CR | Concreting | 26/12/21 | 29/12/21
S-TW-11F-SL BM-CR ZA | Zone A - Slab / beam | 26/12/21 | 26/12/21
S-TW-11F-SL BM-CR ZB | Zone B - Slab / beam | 29/12/21 | 29/12/21
S-TW-12F-- | Level 12 | 27/12/21 | 12/01/22
S-TW-12F-ZZ-CR | Concreting | 09/01/22 | 12/01/22
S-TW-12F-SL BM-CR ZA | Zone A - Slab / beam | 09/01/22 | 09/01/22
S-TW-12F-SL BM-CR ZB | Zone B - Slab / beam | 12/01/22 | 12/01/22
S-TW-13F-- | Level 13 | 10/01/22 | 25/01/22
S-TW-13F-ZZ-CR | Concreting | 22/01/22 | 25/01/22
S-TW-13F-SL BM-CR ZA | Zone A - Slab / beam | 22/01/22 | 22/01/22
S-TW-13F-SL BM-CR ZB | Zone B - Slab / beam | 25/01/22 | 25/01/22
S-TW-14F-- | Level 14 | 23/01/22 | 17/02/22
S-TW-14F-ZZ-CR | Concreting | 14/02/22 | 17/02/22
S-TW-14F-SL BM-CR ZA | Zone A - Slab / beam | 14/02/22 | 14/02/22
S-TW-14F-SL BM-CR ZB | Zone B - Slab / beam | 17/02/22 | 17/02/22
S-TW-15F-- | Level 15 | 15/02/22 | 02/03/22
S-TW-15F-ZZ-CR | Concreting | 27/02/22 | 02/03/22
S-TW-15F-SL BM-CR ZA | Zone A - Slab / beam | 27/02/22 | 27/02/22
S-TW-15F-SL BM-CR ZB | Zone B - Slab / beam | 02/03/22 | 02/03/22
S-TW-16F-- | Level 16 | 28/02/22 | 19/03/22
S-TW-16F-ZZ-CR | Concreting | 09/03/22 | 19/03/22
S-TW-16F-CL-CR ZA | Zone A - column | 09/03/22 | 09/03/22
S-TW-16F-CL-CR ZB | Zone B - column | 12/03/22 | 12/03/22
S-TW-16F-SW-CR CO | Core wall | 12/03/22 | 12/03/22
S-TW-PHF-- | PH | 17/03/22 | 07/04/22
S-TW-PHF-ZZ-CR | Concreting | 27/03/22 | 07/04/22
S-TW-PHF-CL-CR ZA | Zone A - column | 27/03/22 | 27/03/22
S-TW-PHF-CL-CR ZB | Zone B - column | 30/03/22 | 30/03/22
S-TW-PHF-SW-CR LMR | LMR | 29/03/22 | 29/03/22
S-TW-PHF-SL BM-CR ZA | Zone A - Slab / beam | 04/04/22 | 04/04/22
S-TW-PHF-SL BM-CR ZB | Zone B - Slab / beam | 07/04/22 | 07/04/22
S-TW-PHRF-- | PHR | 05/04/22 | 28/04/22
S-TW-LMRF-ZZ-CR | Concreting | 17/04/22 | 28/04/22
S-TW-LMRF-CL-CR ZA | Zone A - column | 17/04/22 | 17/04/22
S-TW-LMRF-SL BM-CR ZA | Zone A - Slab / beam | 25/04/22 | 25/04/22

## ABSERVIATION (hidden)
FIELD # | CODE | MEAN | SPECIFIC VALUE
| ZZ | ALL / UNDEFINED
1 | ACR | ACREDO WAREHOUSE PROJECT
2 | TU | TEMP UTILITIES (MEP)
2 | MB | MOBILIZATON
2 | TP | TEST PILE WORK
2 | PW | PILE WORK
2 | CR | CONCRETE WORK
2 | ST | STEEL
3 | FAC | FACTORY / PRODUCTION
3 | UTI | UTILITY BUILDING
3 | WTB | WASTE BUILDING
4 | GF | GROUND FLOOR | -450mm
4 | 1F | 1ST FLOOR LEVEL | 0 mm
4 | 2F | 2ND FLOOR LEVEL | 7500 mm
4 | 3F | 3RD FLOOR LEVEL
4 | RF | ROOF LEVEL
5 | CL | COLUMN
5 | SL | SLAB
6 | FR | (STEEL) FRAME
6 | RS | ROOF METAL SHEET

## BAK (hidden)
SS | S
SS | S | PD
SS | S | PD | 02F
SS | S | PD | 02F | ZZ | SC
SS | S | PD | 02F | CL | SC ZA
SS | S | PD | 02F | CL | SC ZB
SS | S | PD | 02F | CL | SC ZC
SS | S | PD | 02F | CL | SC ZD
SS | S | PD | 02F | SW | SC
SS | S | PD | 02F | ZZ | RB
SS | S | PD | 02F | CL | RB ZA
SS | S | PD | 02F | CL | RB ZB
SS | S | PD | 02F | CL | RB ZC
SS | S | PD | 02F | CL | RB ZD
SS | S | PD | 02F | SW | RB
SS | S | PD | 02F | ZZ | FW
SS | S | PD | 02F | CL | FW ZA
SS | S | PD | 02F | CL | FW ZB
SS | S | PD | 02F | CL | FW ZC
SS | S | PD | 02F | CL | FW ZD
SS | S | PD | 02F | SW | FW
SS | S | PD | 02F | ZZ | SP
SS | S | PD | 02F | SL | SP ZA
SS | S | PD | 02F | SL | SP ZB
SS | S | PD | 02F | SL | SP ZC
SS | S | PD | 02F | SL | SP ZD
SS | S | PD | 02F | SL | FW
SS | S | PD | 02F | SL | FW ZA
SS | S | PD | 02F | SL | FW ZB
SS | S | PD | 02F | SL | FW ZC
SS | S | PD | 02F | SL | FW ZD
SS | S | PD | 02F | SL | RB
SS | S | PD | 02F | SL | RB ZA
SS | S | PD | 02F | SL | RB ZB
SS | S | PD | 02F | SL | RB ZC
SS | S | PD | 02F | SL | RB ZD