## 02-CODE-TRACK
WI Number | Task Name | Start | Finish | % Complete
| CONSTRUCTION WORKS | 2021-04-26 | 2022-07-31 | 0.2
PD | Podium | 2021-05-02 | 2021-08-20 | 0.97
PD-02F | Level 2 | 2021-05-02 | 2021-06-10 | 1
PD-02F-CL-ZA | Zone A - Column | 2021-05-10 | 2021-05-15 | 1
PD-02F-CL-ZB | Zone B - Column | 2021-05-13 | 2021-05-17 | 1
PD-02F-CL-ZC | Zone C - Column | 2021-05-15 | 2021-05-19 | 1
PD-02F-CL-ZD | Zone D - Column | 2021-05-17 | 2021-05-21 | 1
PD-02F-SW | Core wall | 2021-05-18 | 2021-05-23 | 1
PD-02F-SL-ZA | Zone A - Slab / beam | 2021-06-01 | 2021-06-01 | 1
PD-02F-SL-ZB | Zone B - Slab / beam | 2021-06-03 | 2021-06-03 | 1
PD-02F-SL-ZC | Zone C - Slab / beam | 2021-06-07 | 2021-06-07 | 1
PD-02F-SL-ZD | Zone D - Slab / beam | 2021-06-10 | 2021-06-10 | 1
PD-03F | Level 3 | 2021-06-11 | 2021-07-16 | 1
PD-03F-CL-ZA | Zone A - Column | 2021-06-19 | 2021-06-25 | 1
PD-03F-CL-ZB | Zone B - Column | 2021-06-22 | 2021-06-27 | 1
PD-03F-CL-ZC | Zone C - Column | 2021-06-23 | 2021-06-28 | 1
PD-03F-CL-ZD | Zone D - Column | 2021-06-25 | 2021-06-29 | 1
PD-03F-SW | Core wall | 2021-06-27 | 2021-07-02 | 1
PD-03F-SL-ZA | Zone A - Slab / beam | 2021-07-10 | 2021-07-10 | 1
PD-03F-SL-ZB | Zone B - Slab / beam | 2021-07-12 | 2021-07-12 | 1
PD-03F-SL-ZC | Zone C - Slab / beam | 2021-07-16 | 2021-07-16 | 1
PD-03F-SL-ZD | Zone D - Slab / beam | 2021-07-15 | 2021-07-15 | 1
PD-04F | Level 4 | 2021-07-20 | 2021-08-20 | 0.91
PD-04F-CL-ZA | Zone A - Column | 2021-07-28 | 2021-08-02 | 1
PD-04F-CL-ZB | Zone B - Column | 2021-07-26 | 2021-07-30 | 1
PD-04F-CL-ZC | Zone C - Column | 2021-07-28 | 2021-08-01 | 1
PD-04F-CL-ZD | Zone D - Column | 2021-07-29 | 2021-08-02 | 1
PD-04F-SW | Core wall | 2021-08-05 | 2021-08-10 | 1
PD-04F-SL-ZA | Zone A - Slab / beam | 2021-08-19 | 2021-08-19 | 1
PD-04F-SL-ZB | Zone B - Slab / beam | 2021-08-16 | 2021-08-16 | 1
PD-04F-SL-ZC | Zone C - Slab / beam | 2021-08-20 | 2021-08-20 | 1
PD-04F-SL-ZD | Zone D - Slab / beam | 2021-08-20 | 2021-08-20 | 0
TW | Tower | 2021-08-21 | 2022-04-28 | 0.03
TW-05F | Level 5 | 2021-08-21 | 2021-09-22 | 0.18
TW-05F-CL-ZA | Zone A - Column | 2021-08-31 | 2021-09-05 | 0
TW-05F-CL-ZB | Zone B - Column | 2021-09-03 | 2021-09-07 | 0
TW-05F-SW | Core wall | 2021-09-08 | 2021-09-11 | 0
TW-05F-SLBM-ZA | Zone A - Slab / beam | 2021-09-20 | 2021-09-20 | 0
TW-05F-SLBM-ZB | Zone B - Slab / beam | 2021-09-22 | 2021-09-22 | 0
TW-06F | Level 6 | 2021-09-23 | 2021-10-17 | 0
TW-06F-SLBM-ZA | Zone A - Slab / beam | 2021-10-16 | 2021-10-16 | 0
TW-06F-SLBM-ZB | Zone B - Slab / beam | 2021-10-17 | 2021-10-17 | 0
TW-07F | Level 7 | 2021-10-17 | 2021-11-05 | 0
TW-07F-SLBM-ZA | Zone A - Slab / beam | 2021-11-02 | 2021-11-02 | 0
TW-07F-SLBM-ZB | Zone B - Slab / beam | 2021-11-05 | 2021-11-05 | 0
TW-08F | Level 8 | 2021-11-03 | 2021-11-20 | 0
TW-08F-SLBM-ZA | Zone A - Slab / beam | 2021-11-17 | 2021-11-17 | 0
TW-08F-SLBM-ZB | Zone B - Slab / beam | 2021-11-20 | 2021-11-20 | 0
TW-09F | Level 9 | 2021-11-18 | 2021-12-03 | 0
TW-09F-SLBM-ZA | Zone A - Slab / beam | 2021-11-30 | 2021-11-30 | 0
TW-09F-SLBM-ZB | Zone B - Slab / beam | 2021-12-03 | 2021-12-03 | 0
TW-10F | Level 10 | 2021-12-01 | 2021-12-16 | 0
TW-10F-SLBM-ZA | Zone A - Slab / beam | 2021-12-13 | 2021-12-13 | 0
TW-10F-SLBM-ZB | Zone B - Slab / beam | 2021-12-16 | 2021-12-16 | 0
TW-11F | Level 11 | 2021-12-14 | 2021-12-29 | 0
TW-11F-SLBM-ZA | Zone A - Slab / beam | 2021-12-26 | 2021-12-26 | 0
TW-11F-SLBM-ZB | Zone B - Slab / beam | 2021-12-29 | 2021-12-29 | 0
TW-12F | Level 12 | 2021-12-27 | 2022-01-12 | 0
TW-12F-SLBM-ZA | Zone A - Slab / beam | 2022-01-09 | 2022-01-09 | 0
TW-12F-SLBM-ZB | Zone B - Slab / beam | 2022-01-12 | 2022-01-12 | 0
TW-13F | Level 13 | 2022-01-10 | 2022-01-25 | 0
TW-13F-SLBM-ZA | Zone A - Slab / beam | 2022-01-22 | 2022-01-22 | 0
TW-13F-SLBM-ZB | Zone B - Slab / beam | 2022-01-25 | 2022-01-25 | 0
TW-14F | Level 14 | 2022-01-23 | 2022-02-17 | 0
TW-14F-SLBM-ZA | Zone A - Slab / beam | 2022-02-14 | 2022-02-14 | 0
TW-14F-SLBM-ZB | Zone B - Slab / beam | 2022-02-17 | 2022-02-17 | 0
TW-15F | Level 15 | 2022-02-15 | 2022-03-02 | 0
TW-15F-SLBM-ZA | Zone A - Slab / beam | 2022-02-27 | 2022-02-27 | 0
TW-15F-SLBM-ZB | Zone B - Slab / beam | 2022-03-02 | 2022-03-02 | 0
TW-16F | Level 16 | 2022-02-28 | 2022-03-19 | 0
TW-16F-CL-ZA | Zone A - column | 2022-03-09 | 2022-03-09 | 0
TW-16F-CL-ZB | Zone B - column | 2022-03-12 | 2022-03-12 | 0
TW-16F-SW-CO | Core wall | 2022-03-12 | 2022-03-12 | 0
TW-16F-SLBM-ZA | Zone A - Slab / beam | 2022-03-16 | 2022-03-16 | 0
TW-PHF | PH | 2022-03-17 | 2022-04-07 | 0
TW-PHF-CL-ZA | Zone A - column | 2022-03-27 | 2022-03-27 | 0
TW-PHF-CL-ZB | Zone B - column | 2022-03-30 | 2022-03-30 | 0
TW-PHF-SW-LMR | LMR | 2022-03-29 | 2022-03-29 | 0
TW-PHF-SLBM-ZA | Zone A - Slab / beam | 2022-04-04 | 2022-04-04 | 0
TW-PHF-SLBM-ZB | Zone B - Slab / beam | 2022-04-07 | 2022-04-07 | 0
TW-PHRF | PHR | 2022-04-05 | 2022-04-28 | 0
TW-PHRF-CL-ZA | Zone A - column | 2022-04-17 | 2022-04-17 | 0
TW-PHRF-SLBM-ZA | Zone A - Slab / beam | 2022-04-25 | 2022-04-25 | 0

## 02-CODE-PLAN
WI Number | Task Name | Start | Finish
| SAMSUNG R&D - SUPERSTRUCTURE | 2021-05-02 | 2022-07-31
PDPR | Podium - prior area | 2021-05-02 | 2021-08-20
PDPR-02F | Level 2 | 2021-05-02 | 2021-06-15
PDPR-03F | Level 3 | 2021-06-16 | 2021-07-30
PDPR-04F | Level 4 | 2021-08-03 | 2021-08-20
PDPO | Podium - post area | 2021-08-21 | 2021-10-05
PDPO-02F | Level 2 | 2021-09-06 | 2021-09-15
PDPO-03F | Level 3 | 2021-09-16 | 2021-09-25
PDPO-04F | Level 4 | 2021-09-26 | 2021-10-05
TW | Tower | 2021-08-21 | 2022-04-30
TW-05F | Level 5 | 2021-08-21 | 2021-10-04
TW-06F | Level 6 | 2021-10-05 | 2021-10-24
TW-07F | Level 7 | 2021-10-20 | 2021-11-08
TW-08F | Level 8 | 2021-11-04 | 2021-11-23
TW-09F | Level 9 | 2021-11-19 | 2021-12-08
TW-10F | Level 10 | 2021-12-04 | 2021-12-23
TW-11F | Level 11 | 2021-12-19 | 2022-01-08
TW-12F | Level 12 | 2022-01-04 | 2022-01-23
TW-13F | Level 13 | 2022-01-19 | 2022-02-17
TW-14F | Level 14 | 2022-02-13 | 2022-03-04
TW-15F | Level 15 | 2022-02-28 | 2022-03-19
TW-16F | Level 16 | 2022-03-15 | 2022-04-03
TW-PHF | PH Level | 2022-04-04 | 2022-04-19
TW-PHRF | PH Roof Level | 2022-04-20 | 2022-04-30

## WorkItemData-PLAN
Work Item Number | Work Item Name | Plan Start Date | Plan End Date | Actual Start Date | Acutal End Date / Actual Tracking date | PIC | #NCR | % Complete | Report Date | Quantity Unit | BIM Quantity | QS Quantity | Cost
| SAMSUNG R&D - SUPERSTRUCTURE | 2021-05-02 | 2022-07-31
PDPR | Podium - prior area | 2021-05-02 | 2021-08-20
PDPR-02F | Level 2 | 2021-05-02 | 2021-06-15
PDPR-03F | Level 3 | 2021-06-16 | 2021-07-30
PDPR-04F | Level 4 | 2021-08-03 | 2021-08-20
PDPO | Podium - post area | 2021-08-21 | 2021-10-05
PDPO-02F | Level 2 | 2021-09-06 | 2021-09-15
PDPO-03F | Level 3 | 2021-09-16 | 2021-09-25
PDPO-04F | Level 4 | 2021-09-26 | 2021-10-05
TW | Tower | 2021-08-21 | 2022-04-30
TW-05F | Level 5 | 2021-08-21 | 2021-10-04
TW-06F | Level 6 | 2021-10-05 | 2021-10-24
TW-07F | Level 7 | 2021-10-20 | 2021-11-08
TW-08F | Level 8 | 2021-11-04 | 2021-11-23
TW-09F | Level 9 | 2021-11-19 | 2021-12-08
TW-10F | Level 10 | 2021-12-04 | 2021-12-23
TW-11F | Level 11 | 2021-12-19 | 2022-01-08
TW-12F | Level 12 | 2022-01-04 | 2022-01-23
TW-13F | Level 13 | 2022-01-19 | 2022-02-17
TW-14F | Level 14 | 2022-02-13 | 2022-03-04
TW-15F | Level 15 | 2022-02-28 | 2022-03-19
TW-16F | Level 16 | 2022-03-15 | 2022-04-03
TW-PHF | PH Level | 2022-04-04 | 2022-04-19
TW-PHRF | PH Roof Level | 2022-04-20 | 2022-04-30
#VALUE! | #VALUE! | #VALUE! | #VALUE!
Formulas:
Plan Start Date = _02_CODE_PLAN[[#This Row],[Start]]
Plan End Date = _02_CODE_PLAN[[#This Row],[Finish]]

## WorkItemData-TRACK
Work Item Number | Work Item Name | Plan Start Date | Plan End Date | Actual Start Date | Acutal End Date / Actual Tracking date | PIC | #NCR | % Complete | Report Date | Quantity Unit | BIM Quantity | QS Quantity | Cost
| CONSTRUCTION WORKS |  |  | 2021-04-26 | 2022-07-31 |  |  | 20%
PD | Podium |  |  | 2021-05-02 | 2021-08-20 |  |  | 97%
PD-02F | Level 2 |  |  | 2021-05-02 | 2021-06-10 |  |  | 100%
PD-02F-CL-ZA | Zone A - Column |  |  | 2021-05-10 | 2021-05-15 |  |  | 100%
PD-02F-CL-ZB | Zone B - Column |  |  | 2021-05-13 | 2021-05-17 |  |  | 100%
PD-02F-CL-ZC | Zone C - Column |  |  | 2021-05-15 | 2021-05-19 |  |  | 100%
PD-02F-CL-ZD | Zone D - Column |  |  | 2021-05-17 | 2021-05-21 |  |  | 100%
PD-02F-SW | Core wall |  |  | 2021-05-18 | 2021-05-23 |  |  | 100%
PD-02F-SL-ZA | Zone A - Slab / beam |  |  | 2021-06-01 | 2021-06-01 |  |  | 100%
PD-02F-SL-ZB | Zone B - Slab / beam |  |  | 2021-06-03 | 2021-06-03 |  |  | 100%
PD-02F-SL-ZC | Zone C - Slab / beam |  |  | 2021-06-07 | 2021-06-07 |  |  | 100%
PD-02F-SL-ZD | Zone D - Slab / beam |  |  | 2021-06-10 | 2021-06-10 |  |  | 100%
PD-03F | Level 3 |  |  | 2021-06-11 | 2021-07-16 |  |  | 100%
PD-03F-CL-ZA | Zone A - Column |  |  | 2021-06-19 | 2021-06-25 |  |  | 100%
PD-03F-CL-ZB | Zone B - Column |  |  | 2021-06-22 | 2021-06-27 |  |  | 100%
PD-03F-CL-ZC | Zone C - Column |  |  | 2021-06-23 | 2021-06-28 |  |  | 100%
PD-03F-CL-ZD | Zone D - Column |  |  | 2021-06-25 | 2021-06-29 |  |  | 100%
PD-03F-SW | Core wall |  |  | 2021-06-27 | 2021-07-02 |  |  | 100%
PD-03F-SL-ZA | Zone A - Slab / beam |  |  | 2021-07-10 | 2021-07-10 |  |  | 100%
PD-03F-SL-ZB | Zone B - Slab / beam |  |  | 2021-07-12 | 2021-07-12 |  |  | 100%
PD-03F-SL-ZC | Zone C - Slab / beam |  |  | 2021-07-16 | 2021-07-16 |  |  | 100%
PD-03F-SL-ZD | Zone D - Slab / beam |  |  | 2021-07-15 | 2021-07-15 |  |  | 100%
PD-04F | Level 4 |  |  | 2021-07-20 | 2021-08-20 |  |  | 91%
PD-04F-CL-ZA | Zone A - Column |  |  | 2021-07-28 | 2021-08-02 |  |  | 100%
PD-04F-CL-ZB | Zone B - Column |  |  | 2021-07-26 | 2021-07-30 |  |  | 100%
PD-04F-CL-ZC | Zone C - Column |  |  | 2021-07-28 | 2021-08-01 |  |  | 100%
PD-04F-CL-ZD | Zone D - Column |  |  | 2021-07-29 | 2021-08-02 |  |  | 100%
PD-04F-SW | Core wall |  |  | 2021-08-05 | 2021-08-10 |  |  | 100%
PD-04F-SL-ZA | Zone A - Slab / beam |  |  | 2021-08-19 | 2021-08-19 |  |  | 100%
PD-04F-SL-ZB | Zone B - Slab / beam |  |  | 2021-08-16 | 2021-08-16 |  |  | 100%
PD-04F-SL-ZC | Zone C - Slab / beam |  |  | 2021-08-20 | 2021-08-20 |  |  | 100%
PD-04F-SL-ZD | Zone D - Slab / beam |  |  | 2021-08-20 | 2021-08-20 |  |  | 0%
TW | Tower |  |  | 2021-08-21 | 2022-04-28 |  |  | 3%
TW-05F | Level 5 |  |  | 2021-08-21 | 2021-09-22 |  |  | 18%
TW-05F-CL-ZA | Zone A - Column |  |  | 2021-08-31 | 2021-09-05 |  |  | 0%
TW-05F-CL-ZB | Zone B - Column |  |  | 2021-09-03 | 2021-09-07 |  |  | 0%
TW-05F-SW | Core wall |  |  | 2021-09-08 | 2021-09-11 |  |  | 0%
TW-05F-SLBM-ZA | Zone A - Slab / beam |  |  | 2021-09-20 | 2021-09-20 |  |  | 0%
TW-05F-SLBM-ZB | Zone B - Slab / beam |  |  | 2021-09-22 | 2021-09-22 |  |  | 0%
TW-06F | Level 6 |  |  | 2021-09-23 | 2021-10-17 |  |  | 0%
TW-06F-SLBM-ZA | Zone A - Slab / beam |  |  | 2021-10-16 | 2021-10-16 |  |  | 0%
TW-06F-SLBM-ZB | Zone B - Slab / beam |  |  | 2021-10-17 | 2021-10-17 |  |  | 0%
TW-07F | Level 7 |  |  | 2021-10-17 | 2021-11-05 |  |  | 0%
TW-07F-SLBM-ZA | Zone A - Slab / beam |  |  | 2021-11-02 | 2021-11-02 |  |  | 0%
TW-07F-SLBM-ZB | Zone B - Slab / beam |  |  | 2021-11-05 | 2021-11-05 |  |  | 0%
TW-08F | Level 8 |  |  | 2021-11-03 | 2021-11-20 |  |  | 0%
TW-08F-SLBM-ZA | Zone A - Slab / beam |  |  | 2021-11-17 | 2021-11-17 |  |  | 0%
TW-08F-SLBM-ZB | Zone B - Slab / beam |  |  | 2021-11-20 | 2021-11-20 |  |  | 0%
TW-09F | Level 9 |  |  | 2021-11-18 | 2021-12-03 |  |  | 0%
TW-09F-SLBM-ZA | Zone A - Slab / beam |  |  | 2021-11-30 | 2021-11-30 |  |  | 0%
TW-09F-SLBM-ZB | Zone B - Slab / beam |  |  | 2021-12-03 | 2021-12-03 |  |  | 0%
TW-10F | Level 10 |  |  | 2021-12-01 | 2021-12-16 |  |  | 0%
TW-10F-SLBM-ZA | Zone A - Slab / beam |  |  | 2021-12-13 | 2021-12-13 |  |  | 0%
TW-10F-SLBM-ZB | Zone B - Slab / beam |  |  | 2021-12-16 | 2021-12-16 |  |  | 0%
TW-11F | Level 11 |  |  | 2021-12-14 | 2021-12-29 |  |  | 0%
TW-11F-SLBM-ZA | Zone A - Slab / beam |  |  | 2021-12-26 | 2021-12-26 |  |  | 0%
TW-11F-SLBM-ZB | Zone B - Slab / beam |  |  | 2021-12-29 | 2021-12-29 |  |  | 0%
TW-12F | Level 12 |  |  | 2021-12-27 | 2022-01-12 |  |  | 0%
TW-12F-SLBM-ZA | Zone A - Slab / beam |  |  | 2022-01-09 | 2022-01-09 |  |  | 0%
TW-12F-SLBM-ZB | Zone B - Slab / beam |  |  | 2022-01-12 | 2022-01-12 |  |  | 0%
TW-13F | Level 13 |  |  | 2022-01-10 | 2022-01-25 |  |  | 0%
TW-13F-SLBM-ZA | Zone A - Slab / beam |  |  | 2022-01-22 | 2022-01-22 |  |  | 0%
TW-13F-SLBM-ZB | Zone B - Slab / beam |  |  | 2022-01-25 | 2022-01-25 |  |  | 0%
TW-14F | Level 14 |  |  | 2022-01-23 | 2022-02-17 |  |  | 0%
TW-14F-SLBM-ZA | Zone A - Slab / beam |  |  | 2022-02-14 | 2022-02-14 |  |  | 0%
TW-14F-SLBM-ZB | Zone B - Slab / beam |  |  | 2022-02-17 | 2022-02-17 |  |  | 0%
TW-15F | Level 15 |  |  | 2022-02-15 | 2022-03-02 |  |  | 0%
TW-15F-SLBM-ZA | Zone A - Slab / beam |  |  | 2022-02-27 | 2022-02-27 |  |  | 0%
TW-15F-SLBM-ZB | Zone B - Slab / beam |  |  | 2022-03-02 | 2022-03-02 |  |  | 0%
TW-16F | Level 16 |  |  | 2022-02-28 | 2022-03-19 |  |  | 0%
TW-16F-CL-ZA | Zone A - column |  |  | 2022-03-09 | 2022-03-09 |  |  | 0%
TW-16F-CL-ZB | Zone B - column |  |  | 2022-03-12 | 2022-03-12 |  |  | 0%
TW-16F-SW-CO | Core wall |  |  | 2022-03-12 | 2022-03-12 |  |  | 0%
TW-16F-SLBM-ZA | Zone A - Slab / beam |  |  | 2022-03-16 | 2022-03-16 |  |  | 0%
TW-PHF | PH |  |  | 2022-03-17 | 2022-04-07 |  |  | 0%
TW-PHF-CL-ZA | Zone A - column |  |  | 2022-03-27 | 2022-03-27 |  |  | 0%
TW-PHF-CL-ZB | Zone B - column |  |  | 2022-03-30 | 2022-03-30 |  |  | 0%
TW-PHF-SW-LMR | LMR |  |  | 2022-03-29 | 2022-03-29 |  |  | 0%
TW-PHF-SLBM-ZA | Zone A - Slab / beam |  |  | 2022-04-04 | 2022-04-04 |  |  | 0%
TW-PHF-SLBM-ZB | Zone B - Slab / beam |  |  | 2022-04-07 | 2022-04-07 |  |  | 0%
TW-PHRF | PHR |  |  | 2022-04-05 | 2022-04-28 |  |  | 0%
TW-PHRF-CL-ZA | Zone A - column |  |  | 2022-04-17 | 2022-04-17 |  |  | 0%
TW-PHRF-SLBM-ZA | Zone A - Slab / beam |  |  | 2022-04-25 | 2022-04-25 |  |  | 0%
Formulas:
Actual Start Date = _02_CODE_TRACK[[#This Row],[Start]]
Acutal End Date / Actual Tracking date = _02_CODE_TRACK[[#This Row],[Finish]]

## WorkItemData
Work Item Number | Work Item Name | Plan Start Date | Plan End Date | Actual Start Date | Acutal End Date / Actual Tracking date | PIC | #NCR | % Complete | Report Date | Quantity Unit | BIM Quantity | QS Quantity | Cost
| CONSTRUCTION WORKS |  |  | 2021-04-26 | 2022-07-31 |  |  | 20%
PD | Podium |  |  | 2021-05-02 | 2021-08-20 |  |  | 97%
PD-02F | Level 2 |  |  | 2021-05-02 | 2021-06-10 |  |  | 100%
PD-02F-CL | Podium Level 2 Column
PD-02F-SL | Podium Level 2 Slab
PD-03F-CL | Podium Level 3 Column
PD-03F-SL | Podium Level 3 Slab
PD-04F-CL | Podium Level 4 Column
PD-04F-SL | Podium Level 4 Slab
TW-05F-CL | Tower Level 5 Column
TW-05F-SLBM | Tower Level 5 Slab Beam
TW-06F-SLBM | Tower Level 6 Slab Beam
TW-07F-SLBM | Tower Level 7 Slab Beam
TW-08F-SLBM | Tower Level 8 Slab Beam
TW-09F-SLBM | Tower Level 9 Slab Beam
TW-10F-SLBM | Tower Level 10 Slab Beam
TW-11F-SLBM | Tower Level 11 Slab Beam
TW-12F-SLBM | Tower Level 12 Slab Beam
TW-13F-SLBM | Tower Level 13 Slab Beam
TW-14F-SLBM | Tower Level 14 Slab Beam
TW-15F-SLBM | Tower Level 15 Slab Beam
TW-16F-CL | Tower Level 16 Column
TW-16F-SW | Tower Level 16 Structural Wall
TW-16F-SLBM | Tower Level 16 Slab Beam
TW-PHF-CL | Tower Level Roof Column
TW-PHF-SW | Tower Level Roof Structural Wall
TW-PHF-SLBM | Tower Level Roof Slab Beam
TW-PHRF-CL | Tower Level Top Roof Column
TW-PHRF-SLBM | Tower Level Top Roof Slab Beam
S-PD-02F | Structural Podium Level 2
S-PD-03F | Structural Podium Level 3
S-PD-04F | Structural Podium Level 4
S-TW-05F | Structural Tower Level 5
S-TW-06F | Structural Tower Level 6
S-TW-07F | Structural Tower Level 7
S-TW-08F | Structural Tower Level 8
S-TW-09F | Structural Tower Level 9
S-TW-10F | Structural Tower Level 10
S-TW-11F | Structural Tower Level 11
S-TW-12F | Structural Tower Level 12
S-TW-13F | Structural Tower Level 13
S-TW-14F | Structural Tower Level 14
S-TW-15F | Structural Tower Level 15
S-TW-16F | Structural Tower Level 16
S-TW-PHF | Structural Tower Level Roof
S-TW-PHRF | Structural Tower Level Top Roof
TW-08F-SLBM-ZA | Zone A - Slab / beam |  |  | 2021-11-17 | 2021-11-17 |  |  | 0%
TW-08F-SLBM-ZB | Zone B - Slab / beam |  |  | 2021-11-20 | 2021-11-20 |  |  | 0%
TW-09F | Level 9 |  |  | 2021-11-18 | 2021-12-03 |  |  | 0%
TW-09F-SLBM-ZA | Zone A - Slab / beam |  |  | 2021-11-30 | 2021-11-30 |  |  | 0%
TW-09F-SLBM-ZB | Zone B - Slab / beam |  |  | 2021-12-03 | 2021-12-03 |  |  | 0%
TW-10F | Level 10 |  |  | 2021-12-01 | 2021-12-16 |  |  | 0%
TW-10F-SLBM-ZA | Zone A - Slab / beam |  |  | 2021-12-13 | 2021-12-13 |  |  | 0%
TW-10F-SLBM-ZB | Zone B - Slab / beam |  |  | 2021-12-16 | 2021-12-16 |  |  | 0%
TW-11F | Level 11 |  |  | 2021-12-14 | 2021-12-29 |  |  | 0%
TW-11F-SLBM-ZA | Zone A - Slab / beam |  |  | 2021-12-26 | 2021-12-26 |  |  | 0%
TW-11F-SLBM-ZB | Zone B - Slab / beam |  |  | 2021-12-29 | 2021-12-29 |  |  | 0%
TW-12F | Level 12 |  |  | 2021-12-27 | 2022-01-12 |  |  | 0%
TW-12F-SLBM-ZA | Zone A - Slab / beam |  |  | 2022-01-09 | 2022-01-09 |  |  | 0%
TW-12F-SLBM-ZB | Zone B - Slab / beam |  |  | 2022-01-12 | 2022-01-12 |  |  | 0%
TW-13F | Level 13 |  |  | 2022-01-10 | 2022-01-25 |  |  | 0%
TW-13F-SLBM-ZA | Zone A - Slab / beam |  |  | 2022-01-22 | 2022-01-22 |  |  | 0%
TW-13F-SLBM-ZB | Zone B - Slab / beam |  |  | 2022-01-25 | 2022-01-25 |  |  | 0%
TW-14F | Level 14 |  |  | 2022-01-23 | 2022-02-17 |  |  | 0%
TW-14F-SLBM-ZA | Zone A - Slab / beam |  |  | 2022-02-14 | 2022-02-14 |  |  | 0%
TW-14F-SLBM-ZB | Zone B - Slab / beam |  |  | 2022-02-17 | 2022-02-17 |  |  | 0%
TW-15F | Level 15 |  |  | 2022-02-15 | 2022-03-02 |  |  | 0%
TW-15F-SLBM-ZA | Zone A - Slab / beam |  |  | 2022-02-27 | 2022-02-27 |  |  | 0%
TW-15F-SLBM-ZB | Zone B - Slab / beam |  |  | 2022-03-02 | 2022-03-02 |  |  | 0%
TW-16F | Level 16 |  |  | 2022-02-28 | 2022-03-19 |  |  | 0%
TW-16F-CL-ZA | Zone A - column |  |  | 2022-03-09 | 2022-03-09 |  |  | 0%
TW-16F-CL-ZB | Zone B - column |  |  | 2022-03-12 | 2022-03-12 |  |  | 0%
TW-16F-SW-CO | Core wall |  |  | 2022-03-12 | 2022-03-12 |  |  | 0%
TW-16F-SLBM-ZA | Zone A - Slab / beam |  |  | 2022-03-16 | 2022-03-16 |  |  | 0%
TW-PHF | PH |  |  | 2022-03-17 | 2022-04-07 |  |  | 0%
TW-PHF-CL-ZA | Zone A - column |  |  | 2022-03-27 | 2022-03-27 |  |  | 0%
TW-PHF-CL-ZB | Zone B - column |  |  | 2022-03-30 | 2022-03-30 |  |  | 0%
TW-PHF-SW-LMR | LMR |  |  | 2022-03-29 | 2022-03-29 |  |  | 0%
TW-PHF-SLBM-ZA | Zone A - Slab / beam |  |  | 2022-04-04 | 2022-04-04 |  |  | 0%
TW-PHF-SLBM-ZB | Zone B - Slab / beam |  |  | 2022-04-07 | 2022-04-07 |  |  | 0%
TW-PHRF | PHR |  |  | 2022-04-05 | 2022-04-28 |  |  | 0%
TW-PHRF-CL-ZA | Zone A - column |  |  | 2022-04-17 | 2022-04-17 |  |  | 0%
TW-PHRF-SLBM-ZA | Zone A - Slab / beam |  |  | 2022-04-25 | 2022-04-25 |  |  | 0%
Formulas:
Actual Start Date = _02_CODE_TRACK[[#This Row],[Start]]
Acutal End Date / Actual Tracking date = _02_CODE_TRACK[[#This Row],[Finish]]

## BACKUP (hidden)
WORK ITEM NUMBER | DESCRIPTION | Start | Finish | Actual Start Date | Acutal End Date / Actual Tracking date | PIC | #NCR | % Complete | Report Date | Quantity Unit | BIM Quantity | QS Quantity | Cost
| CONSTRUCTION WORKS | 26/04/21 | 31/07/22
S---- | Structure works | 02/05/21 | 28/04/22
S-PD--- | Podium | 02/05/21 | 20/08/21
S-PD-02F-- | Level 2 | 02/05/21 | 10/06/21
S-PD-02F-ZZ-CR | Concreting | 10/05/21 | 10/06/21
S-PD-02F-CL-CR ZA | Zone A - Column | 10/05/21 | 15/05/21
S-PD-02F-CL-CR ZA B1 | 1st batch | 10/05/21 | 10/05/21
S-PD-02F-CL-CR ZA B2 | 2nd batch | 12/05/21 | 12/05/21
S-PD-02F-CL-CR ZA B3 | 3rd batch | 15/05/21 | 15/05/21
S-PD-02F-CL-CR ZB | Zone B - Column | 13/05/21 | 17/05/21
S-PD-02F-CL-CR ZB B1 | 1st batch | 13/05/21 | 13/05/21
S-PD-02F-CL-CR ZB B2 | 2nd batch | 15/05/21 | 15/05/21
S-PD-02F-CL-CR ZB B3 | 3rd batch | 17/05/21 | 17/05/21
S-PD-02F-CL-CR ZC | Zone C - Column | 15/05/21 | 19/05/21
S-PD-02F-CL-CR ZC B1 | 1st batch | 15/05/21 | 15/05/21
S-PD-02F-CL-CR ZC B2 | 2nd batch | 17/05/21 | 17/05/21
S-PD-02F-CL-CR ZC B3 | 3rd batch | 19/05/21 | 19/05/21
S-PD-02F-CL-CR ZD | Zone D - Column | 17/05/21 | 21/05/21
S-PD-02F-CL-CR ZD B1 | 1st batch | 17/05/21 | 17/05/21
S-PD-02F-CL-CR ZD B2 | 2nd batch | 19/05/21 | 19/05/21
S-PD-02F-CL-CR ZD B3 | 3rd batch | 21/05/21 | 21/05/21
S-PD-02F-SW-CR | Core wall | 18/05/21 | 23/05/21
S-PD-02F-SW-CR zz B1 | 1st batch | 18/05/21 | 18/05/21
S-PD-02F-SW-CR zz B2 | 2nd batch | 23/05/21 | 23/05/21
S-PD-02F-SL-CR ZA | Zone A - Slab / beam | 01/06/21 | 01/06/21
S-PD-02F-SL-CR ZB | Zone B - Slab / beam | 03/06/21 | 03/06/21
S-PD-02F-SL-CR ZC | Zone C - Slab / beam | 07/06/21 | 07/06/21
S-PD-02F-SL-CR ZD | Zone D - Slab / beam | 10/06/21 | 10/06/21
S-PD-03F-- | Level 3 | 11/06/21 | 16/07/21
S-PD-03F-ZZ-CR | Concreting | 19/06/21 | 16/07/21
S-PD-03F-CL-CR ZA | Zone A - Column | 19/06/21 | 25/06/21
S-PD-03F-CL-CR ZA B1 | 1st batch | 19/06/21 | 19/06/21
S-PD-03F-CL-CR ZA B2 | 2nd batch | 21/06/21 | 21/06/21
S-PD-03F-CL-CR ZA B3 | 3rd batch | 25/06/21 | 25/06/21
S-PD-03F-CL-CR ZB | Zone B - Column | 22/06/21 | 27/06/21
S-PD-03F-CL-CR ZB B1 | 1st batch | 22/06/21 | 22/06/21
S-PD-03F-CL-CR ZB B2 | 2nd batch | 24/06/21 | 24/06/21
S-PD-03F-CL-CR ZB B3 | 3rd batch | 27/06/21 | 27/06/21
S-PD-03F-CL-CR ZC | Zone C - Column | 23/06/21 | 28/06/21
S-PD-03F-CL-CR ZC B1 | 1st batch | 23/06/21 | 23/06/21
S-PD-03F-CL-CR ZC B2 | 2nd batch | 25/06/21 | 25/06/21
S-PD-03F-CL-CR ZC B3 | 3rd batch | 28/06/21 | 28/06/21
S-PD-03F-CL-CR ZD | Zone D - Column | 25/06/21 | 29/06/21
S-PD-03F-CL-CR ZD B1 | 1st batch | 25/06/21 | 25/06/21
S-PD-03F-CL-CR ZD B2 | 2nd batch | 27/06/21 | 27/06/21
S-PD-03F-CL-CR ZD B3 | 3rd batch | 29/06/21 | 29/06/21
S-PD-03F-SW-CR | Core wall | 27/06/21 | 02/07/21
S-PD-03F-SW-CR zz B1 | 1st batch | 27/06/21 | 27/06/21
S-PD-03F-SW-CR zz B2 | 2nd batch | 02/07/21 | 02/07/21
S-PD-03F-SL-CR ZA | Zone A - Slab / beam | 10/07/21 | 10/07/21
S-PD-03F-SL-CR ZB | Zone B - Slab / beam | 12/07/21 | 12/07/21
S-PD-03F-SL-CR ZC | Zone C - Slab / beam | 16/07/21 | 16/07/21
S-PD-03F-SL-CR ZD | Zone D - Slab / beam | 15/07/21 | 15/07/21
S-PD-04F-- | Level 4 | 20/07/21 | 20/08/21
S-PD-04F-ZZ-CR | Concreting | 26/07/21 | 20/08/21
S-PD-04F-CL-CR ZA | Zone A - Column | 28/07/21 | 02/08/21
S-PD-04F-CL-CR ZA B1 | 1st batch | 28/07/21 | 28/07/21
S-PD-04F-CL-CR ZA B2 | 2nd batch | 30/07/21 | 30/07/21
S-PD-04F-CL-CR ZA B3 | 3rd batch | 02/08/21 | 02/08/21
S-PD-04F-CL-CR ZB | Zone B - Column | 26/07/21 | 30/07/21
S-PD-04F-CL-CR ZB B1 | 1st batch | 26/07/21 | 26/07/21
S-PD-04F-CL-CR ZB B2 | 2nd batch | 28/07/21 | 28/07/21
S-PD-04F-CL-CR ZB B3 | 3rd batch | 30/07/21 | 30/07/21
S-PD-04F-CL-CR ZC | Zone C - Column | 28/07/21 | 01/08/21
S-PD-04F-CL-CR ZC B1 | 1st batch | 28/07/21 | 28/07/21
S-PD-04F-CL-CR ZC B2 | 2nd batch | 30/07/21 | 30/07/21
S-PD-04F-CL-CR ZC B3 | 3rd batch | 01/08/21 | 01/08/21
S-PD-04F-CL-CR ZD | Zone D - Column | 29/07/21 | 02/08/21
S-PD-04F-CL-CR ZD B1 | 1st batch | 29/07/21 | 29/07/21
S-PD-04F-CL-CR ZD B2 | 2nd batch | 31/07/21 | 31/07/21
S-PD-04F-CL-CR ZD B3 | 3rd batch | 02/08/21 | 02/08/21
S-PD-04F-SW-CR | Core wall | 05/08/21 | 10/08/21
S-PD-04F-SW-CR zz B1 | 1st batch | 05/08/21 | 05/08/21
S-PD-04F-SW-CR zz B2 | 2nd batch | 10/08/21 | 10/08/21
S-PD-04F-SL-CR ZA | Zone A - Slab / beam | 19/08/21 | 19/08/21
S-PD-04F-SL-CR ZB | Zone B - Slab / beam | 16/08/21 | 16/08/21
S-PD-04F-SL-CR ZC | Zone C - Slab / beam | 20/08/21 | 20/08/21
S-PD-04F-SL-CR ZD | Zone D - Slab / beam | 20/08/21 | 20/08/21
S-TW--- | Tower | 21/08/21 | 28/04/22
S-TW-05F-- | Level 5 | 21/08/21 | 22/09/21
S-TW-05F-ZZ-CR | Concreting | 31/08/21 | 22/09/21
S-TW-05F-CL-CR ZA | Zone A - Column | 31/08/21 | 05/09/21
S-TW-05F-CL-CR ZA B1 | 1st batch | 31/08/21 | 31/08/21
S-TW-05F-CL-CR ZA B2 | 2nd batch | 05/09/21 | 05/09/21
S-TW-05F-CL-CR ZB | Zone B - Column | 03/09/21 | 07/09/21
S-TW-05F-CL-CR ZB B1 | 1st batch | 03/09/21 | 03/09/21
S-TW-05F-CL-CR ZB B2 | 2nd batch | 07/09/21 | 07/09/21
S-TW-05F-SW-CR | Core wall | 08/09/21 | 11/09/21
S-TW-05F-SW-CR ZZ B1 | 1st batch | 08/09/21 | 08/09/21
S-TW-05F-SW-CR ZZ B2 | 2nd batch | 11/09/21 | 11/09/21
S-TW-05F-SL BM-CR ZA | Zone A - Slab / beam | 20/09/21 | 20/09/21
S-TW-05F-SL BM-CR ZB | Zone B - Slab / beam | 22/09/21 | 22/09/21
S-TW-06F-- | Level 6 | 23/09/21 | 17/10/21
S-TW-06F-ZZ-CR | Concreting | 16/10/21 | 17/10/21
S-TW-06F-SL BM-CR ZA | Zone A - Slab / beam | 16/10/21 | 16/10/21
S-TW-06F-SL BM-CR ZB | Zone B - Slab / beam | 17/10/21 | 17/10/21
S-TW-07F-- | Level 7 | 17/10/21 | 05/11/21
S-TW-07F-ZZ-CR | Concreting | 02/11/21 | 05/11/21
S-TW-07F-SL BM-CR ZA | Zone A - Slab / beam | 02/11/21 | 02/11/21
S-TW-07F-SL BM-CR ZB | Zone B - Slab / beam | 05/11/21 | 05/11/21
S-TW-08F-- | Level 8 | 03/11/21 | 20/11/21
S-TW-08F-ZZ-CR | Concreting | 17/11/21 | 20/11/21
S-TW-08F-SL BM-CR ZA | Zone A - Slab / beam | 17/11/21 | 17/11/21
S-TW-08F-SL BM-CR ZB | Zone B - Slab / beam | 20/11/21 | 20/11/21
S-TW-09F-- | Level 9 | 18/11/21 | 03/12/21
S-TW-09F-ZZ-CR | Concreting | 30/11/21 | 03/12/21
S-TW-09F-SL BM-CR ZA | Zone A - Slab / beam | 30/11/21 | 30/11/21
S-TW-09F-SL BM-CR ZB | Zone B - Slab / beam | 03/12/21 | 03/12/21
S-TW-10F-- | Level 10 | 01/12/21 | 16/12/21
S-TW-10F-ZZ-CR | Concreting | 13/12/21 | 16/12/21
S-TW-10F-SL BM-CR ZA | Zone A - Slab / beam | 13/12/21 | 13/12/21
S-TW-10F-SL BM-CR ZB | Zone B - Slab / beam | 16/12/21 | 16/12/21
S-TW-11F-- | Level 11 | 14/12/21 | 29/12/21
S-TW-11F-ZZ-CR | Concreting | 26/12/21 | 29/12/21
S-TW-11F-SL BM-CR ZA | Zone A - Slab / beam | 26/12/21 | 26/12/21
S-TW-11F-SL BM-CR ZB | Zone B - Slab / beam | 29/12/21 | 29/12/21
S-TW-12F-- | Level 12 | 27/12/21 | 12/01/22
S-TW-12F-ZZ-CR | Concreting | 09/01/22 | 12/01/22
S-TW-12F-SL BM-CR ZA | Zone A - Slab / beam | 09/01/22 | 09/01/22
S-TW-12F-SL BM-CR ZB | Zone B - Slab / beam | 12/01/22 | 12/01/22
S-TW-13F-- | Level 13 | 10/01/22 | 25/01/22
S-TW-13F-ZZ-CR | Concreting | 22/01/22 | 25/01/22
S-TW-13F-SL BM-CR ZA | Zone A - Slab / beam | 22/01/22 | 22/01/22
S-TW-13F-SL BM-CR ZB | Zone B - Slab / beam | 25/01/22 | 25/01/22
S-TW-14F-- | Level 14 | 23/01/22 | 17/02/22
S-TW-14F-ZZ-CR | Concreting | 14/02/22 | 17/02/22
S-TW-14F-SL BM-CR ZA | Zone A - Slab / beam | 14/02/22 | 14/02/22
S-TW-14F-SL BM-CR ZB | Zone B - Slab / beam | 17/02/22 | 17/02/22
S-TW-15F-- | Level 15 | 15/02/22 | 02/03/22
S-TW-15F-ZZ-CR | Concreting | 27/02/22 | 02/03/22
S-TW-15F-SL BM-CR ZA | Zone A - Slab / beam | 27/02/22 | 27/02/22
S-TW-15F-SL BM-CR ZB | Zone B - Slab / beam | 02/03/22 | 02/03/22
S-TW-16F-- | Level 16 | 28/02/22 | 19/03/22
S-TW-16F-ZZ-CR | Concreting | 09/03/22 | 19/03/22
S-TW-16F-CL-CR ZA | Zone A - column | 09/03/22 | 09/03/22
S-TW-16F-CL-CR ZB | Zone B - column | 12/03/22 | 12/03/22
S-TW-16F-SW-CR CO | Core wall | 12/03/22 | 12/03/22
S-TW-PHF-- | PH | 17/03/22 | 07/04/22
S-TW-PHF-ZZ-CR | Concreting | 27/03/22 | 07/04/22
S-TW-PHF-CL-CR ZA | Zone A - column | 27/03/22 | 27/03/22
S-TW-PHF-CL-CR ZB | Zone B - column | 30/03/22 | 30/03/22
S-TW-PHF-SW-CR LMR | LMR | 29/03/22 | 29/03/22
S-TW-PHF-SL BM-CR ZA | Zone A - Slab / beam | 04/04/22 | 04/04/22
S-TW-PHF-SL BM-CR ZB | Zone B - Slab / beam | 07/04/22 | 07/04/22
S-TW-PHRF-- | PHR | 05/04/22 | 28/04/22
S-TW-LMRF-ZZ-CR | Concreting | 17/04/22 | 28/04/22
S-TW-LMRF-CL-CR ZA | Zone A - column | 17/04/22 | 17/04/22
S-TW-LMRF-SL BM-CR ZA | Zone A - Slab / beam | 25/04/22 | 25/04/22

## ABSERVIATION (hidden)
FIELD # | CODE | MEAN | SPECIFIC VALUE
| ZZ | ALL / UNDEFINED
1 | ACR | ACREDO WAREHOUSE PROJECT
2 | TU | TEMP UTILITIES (MEP)
2 | MB | MOBILIZATON
2 | TP | TEST PILE WORK
2 | PW | PILE WORK
2 | CR | CONCRETE WORK
2 | ST | STEEL
3 | FAC | FACTORY / PRODUCTION
3 | UTI | UTILITY BUILDING
3 | WTB | WASTE BUILDING
4 | GF | GROUND FLOOR | -450mm
4 | 1F | 1ST FLOOR LEVEL | 0 mm
4 | 2F | 2ND FLOOR LEVEL | 7500 mm
4 | 3F | 3RD FLOOR LEVEL
4 | RF | ROOF LEVEL
5 | CL | COLUMN
5 | SL | SLAB
6 | FR | (STEEL) FRAME
6 | RS | ROOF METAL SHEET

## BAK (hidden)
SS | S
SS | S | PD
SS | S | PD | 02F
SS | S | PD | 02F | ZZ | SC
SS | S | PD | 02F | CL | SC ZA
SS | S | PD | 02F | CL | SC ZB
SS | S | PD | 02F | CL | SC ZC
SS | S | PD | 02F | CL | SC ZD
SS | S | PD | 02F | SW | SC
SS | S | PD | 02F | ZZ | RB
SS | S | PD | 02F | CL | RB ZA
SS | S | PD | 02F | CL | RB ZB
SS | S | PD | 02F | CL | RB ZC
SS | S | PD | 02F | CL | RB ZD
SS | S | PD | 02F | SW | RB
SS | S | PD | 02F | ZZ | FW
SS | S | PD | 02F | CL | FW ZA
SS | S | PD | 02F | CL | FW ZB
SS | S | PD | 02F | CL | FW ZC
SS | S | PD | 02F | CL | FW ZD
SS | S | PD | 02F | SW | FW
SS | S | PD | 02F | ZZ | SP
SS | S | PD | 02F | SL | SP ZA
SS | S | PD | 02F | SL | SP ZB
SS | S | PD | 02F | SL | SP ZC
SS | S | PD | 02F | SL | SP ZD
SS | S | PD | 02F | SL | FW
SS | S | PD | 02F | SL | FW ZA
SS | S | PD | 02F | SL | FW ZB
SS | S | PD | 02F | SL | FW ZC
SS | S | PD | 02F | SL | FW ZD
SS | S | PD | 02F | SL | RB
SS | S | PD | 02F | SL | RB ZA
SS | S | PD | 02F | SL | RB ZB
SS | S | PD | 02F | SL | RB ZC
SS | S | PD | 02F | SL | RB ZD